## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
1 | 1 | US-001 | Set up Flask application architecture, modular blueprint routing, and SQLite database schema. | MUST HAVE | No Dependency | Development Team | 3- Completed
1 | 1 | US-002 | Implement candidate registration, authentication, and secure password hashing. | MUST HAVE | US-001 | Development Team | 3- Completed
1 | 1 | US-003 | Build candidate photograph capture module during registration for baseline avatar profile setup. | MUST HAVE | US-002 | Development Team | 3- Completed
1 | 1 | US-004 | Develop examination lifecycle and session management routines for starting, saving, and ending tests. | MUST HAVE | US-001 | Development Team | 3- Completed
1 | 1 | US-005 | Implement synthetic data generation using Faker to populate test sessions for framework validation. | SHOULD HAVE | US-004 | Development Team | 3- Completed
2 | 2 | US-006 | Integrate OpenCV Haar Cascade classifier for continuous face presence monitoring during exam sessions. | MUST HAVE | US-004 | Development Team | 3- Completed
2 | 2 | US-007 | Implement face absence interval tracking to record exact timestamps and durations of unmonitored sessions. | MUST HAVE | US-006 | Development Team | 3- Completed
2 | 2 | US-008 | Calculate dynamic face presence ratio metric throughout active candidate exam sessions. | MUST HAVE | US-007 | Development Team | 3- Completed
2 | 2 | US-009 | Develop client-side JavaScript logging for browser activity, focus loss, tab switching, and fullscreen exit events. | MUST HAVE | US-004 | Development Team | 3- Completed
2 | 2 | US-010 | Implement rule-based suspicious event detection engine with configurable event thresholds. | MUST HAVE | US-007, US-009 | Development Team | 3- Completed
3 | 3 | US-011 | Implement rule-based integrity score calculation engine with weighted suspicious event deductions. | MUST HAVE | US-010 | Development Team | 3- Completed
3 | 3 | US-012 | Develop integrity risk classification module categorizing sessions into Low, Medium, and High risk profiles. | MUST HAVE | US-011 | Development Team | 3- Completed
3 | 3 | US-013 | Integrate LangChain and LLM framework to generate natural-language integrity summaries based on session evidence. | MUST HAVE | US-012 | Development Team | 3- Completed
3 | 3 | US-014 | Build evidence and alert management pipeline for structured storage of violation logs. | MUST HAVE | US-010 | Development Team | 3- Completed
3 | 3 | US-015 | Implement Pandas data analytics for calculating aggregate exam statistics, average integrity, and completion rates. | MUST HAVE | US-014 | Development Team | 3- Completed
3 | 3 | US-016 | Develop statistical visualization pipelines using Matplotlib and Seaborn for session violation distributions. | SHOULD HAVE | US-015 | Development Team | 3- Completed
3 | 3 | US-017 | Implement Scikit-learn K-Means clustering algorithm to perform session and risk profiling across historical attempts. | SHOULD HAVE | US-015 | Development Team | 3- Completed
4 | 4 | US-018 | Develop Streamlit administrative and invigilator dashboard for interactive live monitoring and session analysis. | MUST HAVE | US-015 | Development Team | 3- Completed
4 | 4 | US-019 | Implement report export functionalities supporting structured JSON and CSV downloads for invigilator review. | MUST HAVE | US-018 | Development Team | 3- Completed
4 | 4 | US-020 | Perform end-to-end integration testing, browser compatibility validation, and automated regression suite execution. | MUST HAVE | US-018 | Development Team | 3- Completed
4 | 4 | US-021 | Prepare comprehensive technical project documentation, API references, and clean GitHub repository layout. | MUST HAVE | US-020 | Development Team | 3- Completed

## Sprint Backlog
Sprint | Task ID | US ID | Task Description | Dependency | Priority | Assignee | Status | Deliverable
Sprint 1 | TSK-101 | US-001 | Configure Flask environment, register blueprints, and setup SQLite ORM connection. | None | High | Development Team | 3- Completed | Flask App Blueprint & SQLite DB
Sprint 1 | TSK-102 | US-002 | Create Candidate model schema, signup/login routes, and Werkzeug password hashing. | TSK-101 | High | Development Team | 3- Completed | Auth Routes & User Models
Sprint 1 | TSK-103 | US-003 | Implement HTML5 video stream JS canvas snippet for candidate registration photo capture. | TSK-102 | Medium | Development Team | 3- Completed | Registration Photo Capture View
Sprint 1 | TSK-104 | US-004 | Build database tables and endpoints for Exam and ExamAssignment lifecycle state management. | TSK-101 | High | Development Team | 3- Completed | Exam Lifecycle Endpoints
Sprint 1 | TSK-105 | US-005 | Write Python Faker script to populate database with synthetic student attempts and mock metrics. | TSK-104 | Low | Development Team | 3- Completed | Synthetic Data Generator Script
Sprint 2 | TSK-201 | US-006 | Integrate OpenCV Haar CascadeXml classifier for real-time video frame face detection. | TSK-104 | High | Development Team | 3- Completed | OpenCV Face Presence Pipeline
Sprint 2 | TSK-202 | US-007 | Build backend logic to track continuous face absence start/end timestamps and calculate total duration. | TSK-201 | High | Development Team | 3- Completed | Face Absence Interval Tracker
Sprint 2 | TSK-203 | US-008 | Create formula script computing total face detection duration against total exam elapsed time. | TSK-202 | Medium | Development Team | 3- Completed | Face Presence Ratio Metric
Sprint 2 | TSK-204 | US-009 | Develop frontend JS listeners for visibilitychange, blur, focus, and fullscreen key events. | TSK-104 | High | Development Team | 3- Completed | Browser Monitoring Script
Sprint 2 | TSK-205 | US-010 | Implement rule-engine filtering to parse client event logs and flag threshold breaches. | TSK-202, TSK-204 | High | Development Team | 3- Completed | Suspicious Event Detection Engine
Sprint 3 | TSK-301 | US-011 | Implement weighted deduction model subtracting points based on violation type and duration. | TSK-205 | High | Development Team | 3- Completed | Integrity Scoring Module
Sprint 3 | TSK-302 | US-012 | Implement categorization rules mapping numerical integrity scores into Low, Medium, High risk flags. | TSK-301 | High | Development Team | 3- Completed | Risk Classification Logic
Sprint 3 | TSK-303 | US-013 | Construct LangChain prompt templates parsing structured evidence logs into natural language reports. | TSK-302 | High | Development Team | 3- Completed | LangChain LLM Reporter Module
Sprint 3 | TSK-304 | US-014 | Set up database tables for persistent logging of alerts, violation types, and timestamped evidence. | TSK-205 | Medium | Development Team | 3- Completed | Evidence & Alert Repository
Sprint 3 | TSK-305 | US-015 | Write Pandas analysis routines summarizing candidate performance and monitoring statistics. | TSK-304 | Medium | Development Team | 3- Completed | Pandas Analytics Engine
Sprint 3 | TSK-306 | US-016 | Generate Matplotlib and Seaborn charts displaying class-wide violation frequencies and risk profiles. | TSK-305 | Low | Development Team | 3- Completed | Seaborn Plot Generator Script
Sprint 3 | TSK-307 | US-017 | Train Scikit-learn K-Means model to cluster exam sessions into behavioral anomaly groups. | TSK-305 | Low | Development Team | 3- Completed | K-Means Session Profiler Module
Sprint 4 | TSK-401 | US-018 | Develop multi-page Streamlit web application layout with live invigilator monitoring tables. | TSK-305 | High | Development Team | 3- Completed | Streamlit Admin Dashboard
Sprint 4 | TSK-402 | US-019 | Create JSON and CSV exporter utilities allowing invigilators to download audit reports. | TSK-401 | Medium | Development Team | 3- Completed | JSON/CSV Export Engine
Sprint 4 | TSK-403 | US-020 | Run comprehensive end-to-end integration tests across webcam feeds, browser events, and reporting. | TSK-401 | High | Development Team | 3- Completed | Integration Test Suite Results
Sprint 4 | TSK-404 | US-021 | Finalize project README, setup instructions, code inline comments, and GitHub repository. | TSK-403 | High | Development Team | 3- Completed | Complete GitHub Project Repo

## Stand up Meeting
Sprint | Meeting / Week | Team Member | What was completed? | What is planned next? | Blockers / Issues | Action / Follow-up
Sprint 1 | Week 1 | Development Team | Flask project structure, database models, and SQLite setup. | Implement registration, user login, and password hashing. | Database schema alignment across candidate and session models. | Standardized SQLite table creation scripts and initial migration workflow.
Sprint 1 | Week 2 | Development Team | Candidate authentication, photo capture during registration, and exam lifecycle endpoints. | Integrate OpenCV Haar Cascade face detection pipeline. | Handling camera permissions across different web browser types. | Added fallback UI instructions asking candidates to allow camera access.
Sprint 2 | Week 3 | Development Team | OpenCV Haar Cascade face presence integration and absence tracking logic. | Develop JavaScript client event listeners for browser activity. | Subtle illumination changes causing false face absence triggers. | Adjusted Haar Cascade scaling parameters and set continuous absence time thresholds.
Sprint 2 | Week 4 | Development Team | Browser tab switching, window focus loss, and keypress detection listeners. | Develop rule-based integrity deduction engine. | Duplicate focus-loss events firing simultaneously on browser window switch. | Implemented client-side event debouncing and backend duplicate filtering.
Sprint 3 | Week 5 | Development Team | Weighted integrity score calculation engine and Low/Medium/High risk classification. | Integrate LangChain and LLM framework for natural-language reporting. | Preventing duplicate integrity point deductions for overlapping events. | Unified violation event queue to calculate net score deductions sequentially.
Sprint 3 | Week 6 | Development Team | LangChain LLM summary generation, evidence store, and Pandas analytics script. | Build Streamlit administrative and invigilator dashboard. | LLM API response latency when generating long text reports. | Implemented prompt truncation and structured response formatting for rapid generation.
Sprint 4 | Week 7 | Development Team | Streamlit dashboard views for live monitoring, score displays, and JSON/CSV exports. | Execute full system integration and automated regression tests. | Streamlit auto-refreshing causing temporary lag during heavy data renders. | Optimized Streamlit caching using @st.cache_data for analytics processing.
Sprint 4 | Week 8 | Development Team | Complete system integration testing, automated regression suite execution, and documentation. | Final repository cleanup and submission packaging. | Minor layout glitches on smaller screen resolutions in dashboard view. | Updated CSS layout rules, finalized documentation, and published GitHub repository.

## Retrospection
Sprint | What Went Well | What Could Be Improved | Challenges / Lessons Learned | Action Items | Owner
Sprint 1 | Flask architecture and database schema were configured quickly and cleanly. | Initial database schema lacked flexible fields for storing raw camera frame metadata. | Ensuring database migration consistency early prevents breaking schema updates later. | Maintain modular database migrations and standardized initialization scripts. | Development Team
Sprint 2 | OpenCV Haar Cascade and browser event tracking were successfully integrated. | Occasional duplicate focus-loss logs were recorded during rapid tab switching. | Browser event implementations differ slightly across Chrome, Firefox, and Edge. | Added event debouncing in JavaScript and robust backend event deduplication. | Development Team
Sprint 3 | Integrity scoring rules, K-Means clustering, and LangChain reporting integrated smoothly. | External LLM API call times required handling to avoid endpoint delay. | Formatting unstructured evidence logs into structured LLM prompts is critical for consistent output. | Refined LangChain prompt templates and cached repetitive analytics calculations. | Development Team
Sprint 4 | Streamlit provided an intuitive and responsive admin interface with full export support. | Need for broader manual webcam validation across varied lighting environments. | Proctoring tools require careful calibration between strict detection and avoiding false positives. | Added configurable threshold settings so invigilators can tweak sensitivity. | Development Team